| CPP Critical Path Partners Forensic schedule analysis | CPP-EOT-COVER / CCDC 2 - 2020, Contract No. OCC-B2-2025 (Demo Data) |
| --- | --- |

| Ontario Community College - B2 (Demo Data) Extension of Time Claim — Cover Letter Contractor Northgate Constructors Total Claimed 9 wd Events 1 Date September 01, 2026 | Overall 9 wd |
| --- | --- |

Northgate Constructors

400 Example Road, Toronto, Ontario (Demo)

September 01, 2026

Ms. R. Chen, Owner's Representative (Demo)

Ontario Community College Owner Group

1 College Drive, Toronto, Ontario (Demo)

RE: Extension of Time Claim — Ontario Community College - B2 (Demo Data)

Contract reference: CCDC 2 - 2020, Contract No. OCC-B2-2025 (Demo Data)

Northgate Constructors hereby submits a request for extension of time totalling 9 working days for the above-referenced project. Each delay event is documented in a separate exhibit referenced below.

| Total Claimed 9 wd extension of time | Delay Events 1 exhibits B onward | Supporting Docs 5 D / E series | Response Due 30 d per contract |
| --- | --- | --- | --- |

A-01   Exhibit Index

| Exhibit | Title | File |
| --- | --- | --- |
| A | Cover Letter (this document) | — |
| DE-01 | Delay Event Analysis: Fire-spray application held for owner inspector availability | Ontario_Community_College___B2_Demo_Data_Exhibit_DE-01_Fire_spray_application_held_for_owner_inspector_availability.docx |
| Workbook | Forensic Schedule Workbook | — |
| Index | Supporting Documents Index | — |

A-02   Entitlement Summary

| Exhibit | Window | Description | Working Days |
| --- | --- | --- | --- |
| DE-01 | Baseline → Current | Fire-spray application held for owner inspector availability | 9 wd |
| — |  | TOTAL CLAIMED | 9 wd |

A-03   Contract Basis

The Contractor claims 9 working days pursuant to GC 6.5.1 (delay by the Owner or the Consultant) of the demonstration contract. Clause citations follow the demonstration contract and are stated for format; this is synthetic data.

| Exhibit | Event | Contract Clause(s) |
| --- | --- | --- |
| DE-01 | Fire-spray application held for owner inspector availability | GC 6.5.1 (delay by the Owner or the Consultant) |

A-04   Closing

We request a formal written response to this claim within 30 days in accordance with the contract. Please contact the undersigned with any questions or to schedule a meeting to discuss this submission.

Respectfully submitted,

Dana Fitkowski

Principal, Critical Path Partners

Northgate Constructors

CC: Project file. 1 delay event analyses. Forensic schedule workbook. Supporting documents index (5 docs).