## Summary
CPP . CRITICAL PATH PARTNERS |  |  |  |  | DWG . CPP-CLM-0001 / SHEET A-00
Forensic Schedule Workbook, Ontario Community College - B2 (Demo Data)
Generated 01 Sep 2026
PROJECT: Forensic Schedule Workbook, Ontario Community College - B2 (Demo Data) |  | DATA DATE: 01 Sep 2026 |  | SHEET: A-00
Exhibit | Window | Delay Event | Gross WD | Concurrent WD | Net WD Claimed | Contract Clauses
DE-01 | Baseline → Current | Fire-spray application held for owner inspector availability | 9 | 0 | 9 | GC 6.5.1 (delay by the Owner or the Consultant)
— |  | TOTAL |  |  | 9
Generated 01 Sep 2026 . Project Ontario Community College - B2 (Demo Data) . Net WD claimed (sum) 9d . All delay events listed, never truncated. . Engine cpm-engine v2.9.42 | [5 empty] | Reproducible . Engineered for Daubert scrutiny

## W1 Baseline -> Current
CPP . CRITICAL PATH PARTNERS | [5 empty] | DWG . CPP-CLM-0001 / SHEET A-01
Window 1: Baseline → Current
Per-window slip register, all slipped activities listed
PROJECT: Window 1: Baseline → Current |  | DATA DATE: 2025-07-01 |  | SHEET: A-01
Period | 2025-04-01 -> 2025-07-01
Completion shift this window (wd) | 21 working days
Cumulative shift vs baseline (wd) | 21 working days
CP duration growth (count) | 15
Slipped activities (count) | 309
Newly critical (count) | 28
Activity | Name | Prior Finish | Later Finish | Slip | Responsible Party | Cause Notes | On CP
A4070 | Frames installation | 2025-09-30 | 2026-06-19 | 182 | Contractor | Frame installation at the end of the delayed interior chain | Yes
A4060 | Blocking | 2025-10-07 | 2026-06-09 | 169 | Contractor | Blocking follows sprinkler rough-in in the interior chain | Yes
A4050 | Sprinkler Rough-ins | 2025-10-07 | 2026-05-29 | 162 | Contractor | Sprinkler rough-in follows partition framing; trade stacking on remobilization | Yes
A4030 | New Partition Framing | 2025-09-23 | 2026-04-08 | 136 | Contractor | Framing crew availability following remobilization | Yes
A3850 | Foundations | 2025-08-22 | 2026-02-23 | 126 | Owner | Differing site condition at the existing facade tie-in
A3860 | Concrete Vertical Piers | 2025-08-29 | 2026-03-02 | 126 | Owner | Follows delayed foundations at the tie-in
A3870 | Removal of Existing Facade for Tie In | 2025-09-03 | 2026-03-05 | 126 | Owner | Existing facade removal held for tie-in condition resolution
A3880 | Structural Steel erection including expansion plates | 2025-11-10 | 2026-03-26 | 94 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3890 | Envelope | 2025-12-15 | 2026-04-30 | 94 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A4150 | New Exterior Paved Areas and Sidewalks | 2026-01-14 | 2026-05-29 | 94 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A4160 | Landscape Installations | 2026-01-28 | 2026-06-12 | 94 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3940 | Existing Slab Removal and Trenching | 2025-06-19 | 2025-10-28 | 90 | Contractor | Resequenced slab removal and trenching
A3900 | Interior M&E Rough in | 2026-01-14 | 2026-05-14 | 84 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2090 | 23 52 16 - Heating Boilers | 2025-12-01 | 2026-03-16 | 71 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3910 | Interior Finishes | 2026-02-11 | 2026-05-15 | 65 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2730 | Stairs B Installation @ North Side | 2025-11-19 | 2026-02-18 | 62 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1710 | Misc. Metals | 2025-10-29 | 2026-01-27 | 62 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2720 | Tactile Attention Indicators Mock-up | 2025-10-30 | 2026-01-28 | 62 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1500 | 23 52 16 - Heating Boilers | 2025-07-23 | 2025-10-21 | 62 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1950 | 23 82 19 - Fan Coil Units | 2025-11-26 | 2026-02-25 | 62 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2050 | 23 25 00 - Water Treatment | 2025-11-12 | 2026-02-09 | 61 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2060 | 23 37 13 - Diffuser and Grilles | 2025-12-05 | 2026-03-05 | 60 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3270 | New Stair A Installation | 2025-11-17 | 2026-02-10 | 59 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2540 | Compaction Inspection | 2025-08-22 | 2025-11-14 | 58 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2180 | 26 09 23 - Lighting Control | 2025-11-05 | 2026-01-23 | 55 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3170 | Install Built-up Roof | 2025-12-17 | 2026-03-09 | 54 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1130 | Misc. Metals Shop Drawings | 2025-07-18 | 2025-10-02 | 53 | Contractor | Late misc. metals submittal
A3180 | Roof Inspection | 2025-12-19 | 2026-03-09 | 52 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1680 | Structural Steel | 2025-07-25 | 2025-10-02 | 48 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1160 | TPO Roofing Shop Drawings | 2025-06-19 | 2025-08-26 | 47 | Owner | Owner-directed revision to the roofing assembly; resubmittal and re-review cycle
A1740 | TPO Roofing (Bridge) | 2025-08-04 | 2025-10-08 | 46 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1330 | Fall Arrest Anchors and Horizontal Lines | 2025-07-25 | 2025-09-29 | 45 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2640 | Install Roof Decking | 2025-11-12 | 2026-01-15 | 44 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2630 | Install Roof Anchors | 2025-11-05 | 2026-01-08 | 44 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1920 | Fall Arrest Anchors and Horizontal Lines | 2025-10-22 | 2025-12-23 | 44 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3150 | Roof Parapet Framing | 2025-11-19 | 2026-01-22 | 44 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3160 | Roof Penetration Layout | 2025-11-14 | 2026-01-19 | 44 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2510 | Supply of Embedment & Ankors | 2025-06-20 | 2025-08-22 | 44 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2580 | Underground Drainage | 2025-09-08 | 2025-11-07 | 43 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2130 | 22 40 00 - Plumbing Fixtures | 2025-12-03 | 2026-02-03 | 42 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3930 | Interior Demolition | 2025-07-07 | 2025-09-02 | 40 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2590 | Backfilling to U/S of SOG | 2025-09-19 | 2025-11-14 | 39 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1970 | 23 21 23 - Pumps | 2025-11-17 | 2026-01-12 | 38 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1590 | 26 09 23 - Lighting Control (R0) | 2025-06-26 | 2025-08-18 | 36 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2150 | 26 50 00 - Lighting Fixtures | 2025-11-20 | 2026-01-12 | 35 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2220 | Testing and Inspection Cash Allowance Expenditure | 2025-05-13 | 2025-07-02 | 34 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1960 | 23 74 13 - Air Handling Units | 2026-03-30 | 2026-05-15 | 34 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2440 | Formwork Remaining Pad Footing (Ramp) | 2025-07-30 | 2025-09-17 | 34 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A4040 | MEP Rough-ins | 2026-03-25 | 2026-05-11 | 33 | Contractor | MEP rough-in trade coordination; stacked trades after remobilization | Yes
A4080 | Drywall/Sheathing Installation | 2026-05-19 | 2026-07-06 | 33 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A4090 | Taping and mudding | 2026-06-02 | 2026-07-20 | 33 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A4110 | Tile and Rubber Flooring Installation | 2026-06-12 | 2026-07-30 | 33 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A4100 | Painting | 2026-06-05 | 2026-07-23 | 33 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A4120 | Final Terminations and Fixtures Installation | 2026-06-19 | 2026-08-06 | 33 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A2120 | 20 05 10 - Electric Heat Tracing | 2025-12-01 | 2026-01-19 | 33 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A4170 | Fire Alarm Verification | 2026-07-07 | 2026-08-20 | 32 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1110 | Structural Reinforcement + Decking Shop Drawings | 2025-06-19 | 2025-08-01 | 30 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1290 | Suspended Metal Soffits | 2025-07-25 | 2025-09-04 | 28 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1820 | Coiling Doors | 2025-12-03 | 2026-01-14 | 28 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1870 | ACT & ACB | 2025-09-09 | 2025-10-17 | 27 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1460 | 23 25 00 - Water Treatment (R0) | 2025-07-04 | 2025-08-12 | 27 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1580 | 26 50 00 - Lighting Fixtures | 2025-07-14 | 2025-08-18 | 25 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1700 | Cold-formed Metal Framing | 2025-07-04 | 2025-08-07 | 24 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1120 | Cold-formed Metal Framing Shop Drawings | 2025-06-19 | 2025-07-23 | 23 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1220 | Flush Wood Doors Sample | 2025-07-25 | 2025-08-27 | 23 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1280 | ACT Data sheet and Sample | 2025-07-25 | 2025-08-27 | 23 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A4240 | Minor Deficiencies & Touch-ups | 2026-08-28 | 2026-09-30 | 22 | Contractor | Deficiency and touch-up re-work extended by finishing crew quality issues | Yes
A1810 | Flush Wood Doors | 2025-11-12 | 2025-12-12 | 22 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A4260 | Total Completion | 2026-08-31 | 2026-09-30 | 21 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A4220 | Final Cleaning | 2026-08-05 | 2026-09-03 | 21 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A4180 | Mechanical, Electrical and Elevator Commissioning | 2026-07-29 | 2026-08-27 | 21 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A4190 | Integrated Testing | 2026-08-12 | 2026-09-11 | 21 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A4250 | Ready-To-Take Over | 2026-08-31 | 2026-09-30 | 21 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A4230 | Close-out Documents & Training | 2026-08-05 | 2026-09-03 | 21 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A4210 | Occupancy | 2026-08-13 | 2026-09-11 | 20 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A2500 | Install Rebar for Piers | 2025-08-08 | 2025-09-08 | 20 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A4200 | Substantial Performance | 2026-08-14 | 2026-09-11 | 19 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A1230 | Coiling Doors | 2025-07-25 | 2025-08-21 | 19 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1180 | Exterior Wall Cladding Shop Drawings | 2025-08-11 | 2025-09-05 | 18 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1210 | Interior Aluminum Screen | 2025-07-25 | 2025-08-20 | 18 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1760 | Exterior Wall Cladding | 2025-11-05 | 2025-12-01 | 18 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1800 | Interior Aluminum Screens | 2025-12-03 | 2025-12-29 | 17 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1090 | Masonry and Mortar Samples & Data Sheets | 2025-07-25 | 2025-08-18 | 16 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1100 | Structural Steel Framing and Steel Deck Shop Drawings (R0) | 2025-06-19 | 2025-07-14 | 16 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2550 | Form and Pour Grade Beams | 2025-09-08 | 2025-09-30 | 16 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2560 | Below Grade Vapour Barrier Mock-up | 2025-09-09 | 2025-10-01 | 16 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2570 | Footing Vapor Barrier & Insulation | 2025-09-12 | 2025-10-06 | 16 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2750 | L1, L2 & L3 Framing and Sheathing Installation | 2025-12-05 | 2025-12-29 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A2880 | L1, L2 & L3 Framing and Sheathing Installation | 2025-12-19 | 2026-01-13 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A2890 | L1 Masonry Wall Installation | 2025-12-29 | 2026-01-20 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2770 | L1 Masonry Wall installation | 2025-12-09 | 2025-12-31 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2790 | L1, L2 & L3 Air Vapour Barrier Installation | 2025-12-12 | 2026-01-06 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3260 | Seal Concrete Floor | 2026-03-04 | 2026-03-25 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A3430 | Seal concrete Floor | 2026-03-06 | 2026-03-27 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3280 | New partition framing | 2026-03-18 | 2026-04-08 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3330 | Door frames Installation | 2026-03-25 | 2026-04-15 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3440 | New partition framing | 2026-04-01 | 2026-04-22 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3560 | Seal concrete Floor | 2026-03-12 | 2026-04-02 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1670 | Masonry and Mortar | 2025-08-04 | 2025-08-25 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3420 | Fire Spraying & Intumescent Paint | 2026-03-04 | 2026-03-25 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3550 | Fire Spraying & Intumescent Paint | 2026-03-11 | 2026-04-01 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2820 | Glazing Site Measure and Scanning | 2025-12-08 | 2025-12-30 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2280 | Under Pinning Inspection | 2025-06-20 | 2025-07-14 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2760 | Masonry Mock-up | 2025-12-08 | 2025-12-30 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2740 | Cold-Formed Metal Framing Mock | 2025-12-01 | 2025-12-22 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3680 | Misc. Metals Mock-up | 2026-04-02 | 2026-04-23 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2780 | Above Grade Vapour Mock-up | 2025-12-08 | 2025-12-30 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2800 | AVB Inspection | 2025-12-08 | 2025-12-30 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3250 | Fire Spraying & Intumescent Paint Inspection | 2026-02-25 | 2026-03-19 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A2520 | Form and Pour Foundation Piers | 2025-08-15 | 2025-09-08 | 15 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3490 | Door frames Installation | 2026-04-07 | 2026-04-27 | 14 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3520 | Door and Hardware Installation | 2026-04-21 | 2026-05-11 | 14 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3620 | Door frames Installation | 2026-04-23 | 2026-05-13 | 14 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3570 | New wall partition framing | 2026-04-16 | 2026-05-06 | 14 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3920 | Setup Temporary Hoarding | 2025-06-13 | 2025-07-04 | 14 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3240 | Fire Spraying & Intumescent Paint | 2026-02-25 | 2026-03-18 | 14 | Owner | Fire-spray application held for owner inspector availability | Yes
A3210 | Electrical and Mechanical Room | 2026-03-04 | 2026-03-24 | 14 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3690 | Misc. Metals installation | 2026-05-29 | 2026-06-18 | 14 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3220 | Mech. and Elec. Equipment Installation | 2026-03-18 | 2026-04-07 | 14 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1530 | 20 05 10 - Electric Heat Tracing (R0) | 2025-07-23 | 2025-08-12 | 14 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2530 | Backfilling to U/S of Grade Beams | 2025-08-22 | 2025-09-12 | 14 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1060 | Foundation Concrete Rebar Shop Drawing | 2025-06-19 | 2025-07-08 | 12 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1050 | Ductbank Underpinning Drawing | 2025-06-12 | 2025-06-30 | 12 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1470 | 23 37 13 - Diffuser and Grilles Shop Drawings (R0) | 2025-07-29 | 2025-08-14 | 12 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3410 | Painting | 2026-05-07 | 2026-05-25 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3300 | Electrical, FA & Comms rough-ins | 2026-04-06 | 2026-04-21 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3320 | Blocking Installation | 2026-04-09 | 2026-04-24 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3350 | Gypsum board Installation | 2026-04-16 | 2026-05-01 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3360 | Drywall Taping and Mudding | 2026-04-30 | 2026-05-15 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3390 | Interior Aluminum/Glazing Screens Installation | 2026-05-07 | 2026-05-25 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3370 | Door and Hardware Installation | 2026-05-07 | 2026-05-25 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3810 | Install Controller at Machine Room | 2026-05-08 | 2026-05-26 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3820 | Rails and Elevator Car installation | 2026-05-25 | 2026-06-09 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3830 | Power to controller, Phone lines and Comms | 2026-06-01 | 2026-06-16 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3840 | Elevator Testing and Commissioning | 2026-06-22 | 2026-07-08 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3380 | Interior Aluminum/Glazing Screens Mock-up | 2026-05-01 | 2026-05-19 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3340 | ACT Baffles Mock-ups | 2026-04-10 | 2026-04-27 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3400 | Paint Mock-up | 2026-05-05 | 2026-05-21 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1560 | 26 50 00 - Emergency Lighting & Exit Signs | 2025-07-14 | 2025-07-29 | 11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3290 | Mech. & Plumbing rough-ins | 2026-04-01 | 2026-04-15 | 10 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3310 | Sprinkler Rough-ins | 2026-04-01 | 2026-04-15 | 10 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3540 | Painting | 2026-05-20 | 2026-06-02 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2610 | Erect Structural Steel | 2025-10-20 | 2025-10-31 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2650 | Install Level 2 & 3 Decking | 2025-11-03 | 2025-11-14 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3450 | Mech. & Plumbing rough-ins | 2026-04-16 | 2026-04-29 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3480 | Blocking Installation | 2026-04-23 | 2026-05-06 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3500 | Gypsum board Installation | 2026-04-30 | 2026-05-13 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3460 | Electrical, FA & Comms rough-ins | 2026-04-20 | 2026-05-01 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3510 | Drywall Taping and Mudding | 2026-05-14 | 2026-05-28 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3530 | Interior Glazing Installation | 2026-05-22 | 2026-06-04 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3590 | Electrical, FA & Comms rough-ins | 2026-04-27 | 2026-05-08 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3580 | Mech. & Plumbing rough-ins | 2026-04-09 | 2026-04-22 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3610 | Blocking Installation | 2026-05-04 | 2026-05-15 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3470 | Sprinkler Rough-ins | 2026-04-16 | 2026-04-29 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3600 | Sprinkler Rough-ins | 2026-04-09 | 2026-04-22 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2660 | Install Temporary Hoarding for Slab on Deck | 2025-11-03 | 2025-11-14 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2620 | Structural Steel Inspection | 2025-10-20 | 2025-10-31 | 9 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1080 | Bentonite Waterstop Data Sheet | 2025-06-19 | 2025-07-02 | 8 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1660 | Bentonite Waterstop | 2025-06-26 | 2025-07-09 | 8 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2140 | 26 27 26 - Wiring Devices, Service Poles, & Floor Boxes | 2025-11-05 | 2025-11-17 | 8 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1550 | 26 27 26 - Wiring Devices, Service Poles, & Floor Boxes | 2025-06-26 | 2025-07-08 | 7 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3750 | Washroom Partitions and Accessories Installation | 2026-07-08 | 2026-07-16 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2670 | Rebar and Prep Work for Slab on Deck | 2025-11-10 | 2025-11-18 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3110 | L1, L2 & L3 Exterior Glazing Installation (W09a, W09b) | 2026-03-26 | 2026-04-03 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2930 | L1, L2 & L3 Exterior Glazing Installation (W07a, W07b, W01, W02 & W03) | 2026-03-12 | 2026-03-20 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2840 | L1, L2, L3 Exterior Glazing Installation (W05) | 2026-03-05 | 2026-03-13 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3010 | L2 & L3 Exterior Glazing Installation (W08a, W08b) | 2026-03-05 | 2026-03-13 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3720 | Ceiling/Wall Fixtures Installation | 2026-06-30 | 2026-07-09 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3740 | Millwork Installation | 2026-06-23 | 2026-07-02 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3710 | Tiling and rubber flooring Installation | 2026-06-30 | 2026-07-09 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3670 | Painting | 2026-06-16 | 2026-06-24 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3770 | Corner Guards and Wall Protection Installation | 2026-07-06 | 2026-07-14 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3660 | Interior Glazing Installation | 2026-06-09 | 2026-06-17 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3650 | Door and Hardware Installation | 2026-06-16 | 2026-06-24 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3630 | Gypsum board Installation | 2026-05-19 | 2026-05-27 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3640 | Drywall Taping and Mudding | 2026-06-02 | 2026-06-10 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2850 | Exterior Cladding Site Measure and Scanning | 2026-03-06 | 2026-03-16 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2940 | Exterior Cladding Site Measure and Scanning | 2026-03-13 | 2026-03-23 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3020 | Exterior Cladding Site Measure and Scanning | 2026-03-06 | 2026-03-16 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3100 | Glazing Shop Fabrication | 2026-03-19 | 2026-03-27 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3120 | Exterior Cladding Site Measure and Scanning | 2026-03-27 | 2026-04-06 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3760 | Plumbing Washroom Fixtures Installation | 2026-07-08 | 2026-07-16 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3730 | Millwork Mock-up | 2026-06-17 | 2026-06-25 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2810 | Aluminum & Metal Panel Cladding Mock-up | 2026-03-06 | 2026-03-16 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3700 | Tiling & Rubber & Carpet Flooring Mock-up | 2026-06-17 | 2026-06-25 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1370 | 23 74 13 - Air Handling Units (R0) | 2025-07-11 | 2025-07-21 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2030 | 23 81 26 - Split System | 2025-11-18 | 2025-11-26 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2160 | 27 10 00 - Structural Cabling System (Fiber Optic Cable) | 2026-04-21 | 2026-04-29 | 6 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2680 | Concrete pour for slab on deck level 2 & 3 | 2025-11-13 | 2025-11-20 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2960 | L2 & L3 Cladding Installation (EW2) | 2026-05-11 | 2026-05-19 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2870 | L1, L2 & L3 Cladding Installation (EW2a) | 2026-05-04 | 2026-05-11 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3040 | L2 & L3 Cladding Installation (EW2) | 2026-05-04 | 2026-05-11 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3050 | Horizontal Shading Louvers | 2026-05-11 | 2026-05-19 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2900 | Air Vapor Barrier Installation | 2026-01-13 | 2026-01-20 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3140 | L1, L2 & L3 Cladding Installation (EW2, EW2A) | 2026-06-02 | 2026-06-09 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3070 | L1, L2 & L3 Air Vapor Barrier Installation | 2026-02-25 | 2026-03-05 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2690 | Final Grading and Vapor Barrier for SOG | 2025-11-18 | 2025-11-25 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2860 | Exterior Cladding Shop Fabrication | 2026-04-06 | 2026-04-13 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2910 | Glazing Site Measure and Scanning | 2026-01-07 | 2026-01-14 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2950 | Exterior Cladding Shop Fabrication | 2026-04-13 | 2026-04-20 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3000 | Glazing Shop Fabrication | 2026-02-26 | 2026-03-06 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3030 | Exterior Cladding Shop Fabrication | 2026-04-06 | 2026-04-13 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3130 | Exterior Cladding Shop Fabrication | 2026-04-27 | 2026-05-04 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3080 | L1, L2 & L3 Air Vapor Barrier Inspection | 2026-02-25 | 2026-03-05 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1420 | 23 57 00 - Heat Exchangers | 2025-06-25 | 2025-07-03 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1570 | 27 10 00 - Structural Cabling System (Fiber Optic Cable) | 2025-07-15 | 2025-07-22 | 5 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2970 | L2 & L3 Framing and Sheathing Installation | 2026-01-27 | 2026-02-02 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A3060 | L1, L2 & L3 Framing and Sheathing Installation | 2026-02-18 | 2026-02-24 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A2980 | L2 & L3 Air Vapor Barrier Installation | 2026-02-03 | 2026-02-09 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1070 | Foundation Concrete Mix Design | 2025-06-19 | 2025-06-25 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1650 | Foundation Concrete Mix Design | 2025-06-23 | 2025-06-27 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2830 | Glazing Shop Fabrication | 2026-01-21 | 2026-01-27 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2920 | Glazing Shop Fabrication | 2026-02-04 | 2026-02-10 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2990 | Glazing Site Measure and Scanning | 2026-01-28 | 2026-02-03 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3090 | Glazing Site Measure and Scanning | 2026-02-19 | 2026-02-25 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3230 | Fire Spraying & Intumescent Paint Mock-up | 2026-02-19 | 2026-02-25 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1510 | 23 00 00 - Wall Fin Heater | 2025-08-06 | 2025-08-12 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1540 | 22 40 00 - Plumbing Fixtures (R0) | 2025-07-25 | 2025-07-31 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2100 | 23 00 00 - Wall Fin Heater | 2025-12-12 | 2025-12-18 | 4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1040 | Permit (Not Required Per Ontario Community College) | 2025-05-13 | 2025-05-16 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1030 | IFC Drawings Released | 2025-05-12 | 2025-05-15 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1150 | Built-up Roofing Shop Drawings | 2025-07-04 | 2025-07-09 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1170 | Air Barrier System Data Sheet and Mockup | 2025-07-04 | 2025-07-09 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1190 | Fire-resistive Material Data Sheet | 2025-07-04 | 2025-07-09 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1350 | Sprinkler & Standpipe Shop Drawings | 2025-07-11 | 2025-07-16 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1730 | Built-up Roofing | 2025-08-18 | 2025-08-21 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1750 | Air Barrier System | 2025-07-18 | 2025-07-23 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1770 | Fire-resistive Material | 2025-08-04 | 2025-08-07 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1940 | Sprinkler & Standpipe Shop Drawings | 2025-08-04 | 2025-08-07 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2710 | Concrete Pour and Curing for SOG | 2025-11-28 | 2025-12-03 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2700 | Rebar Installation for SOG | 2025-11-21 | 2025-11-26 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3190 | Hoisting Roof Equipment | 2026-06-09 | 2026-06-12 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3200 | Roof Anchor System Installation | 2026-06-16 | 2026-06-19 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1390 | 23 25 00 - Buffer Tanks | 2025-06-27 | 2025-07-03 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1400 | 23 21 16 - Air Separator | 2025-06-27 | 2025-07-03 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1410 | 23 21 16 - Expansion Tanks | 2025-06-27 | 2025-07-03 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1520 | 23 74 13 - Air Source Heat Pump | 2025-07-14 | 2025-07-17 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2110 | 23 74 13 - Air Source Heat Pump | 2026-06-02 | 2026-06-05 | 3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2240 | Construction Site Setup. Fencing and Temp Facilities | 2025-06-12 | 2025-06-16 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1010 | Contract Award | 2025-04-30 | 2025-05-02 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2230 | Ontario Community College Auto Show | 2025-06-05 | 2025-06-09 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2270 | Excavation for Under Pinning | 2025-06-19 | 2025-06-23 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2250 | Tree Removal, Protection and Equipment Mobilization | 2025-06-13 | 2025-06-17 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2260 | Top Soil Stripping | 2025-06-18 | 2025-06-20 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2300 | Setup Hoarding @ Vestibule F100 | 2025-06-16 | 2025-06-18 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2320 | Demolition of Existing Vestibule F100 | 2025-06-23 | 2025-06-25 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2290 | Existing Structure Under Pinning | 2025-07-11 | 2025-07-15 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2330 | Gas Meter and Pipe Relocation Investigation | 2025-06-17 | 2025-06-19 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2340 | Gas Meter and pipe Relocation | 2025-06-19 | 2025-06-23 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2350 | Daylighting of Existing Hydro Ductbank & Services | 2025-07-03 | 2025-07-07 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1020 | Subcontract Award | 2025-05-29 | 2025-06-02 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1140 | Millwork Shop Drawings | 2025-07-25 | 2025-07-29 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1200 | Hollow Metal Frames & Doors Shop Drawings | 2025-07-25 | 2025-07-29 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1240 | Aluminum Framed Glazing System Shop Drawings | 2025-08-04 | 2025-08-06 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1250 | Finished Hardware Schedule | 2025-07-25 | 2025-07-29 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1260 | Stud framing and Gypsum Board Data Sheets | 2025-07-25 | 2025-07-29 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1270 | Tiling Data sheet and samples | 2025-07-25 | 2025-07-29 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1300 | Flooring Data Sheets and Samples | 2025-07-25 | 2025-07-29 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1310 | Paint Drawdowns | 2025-07-25 | 2025-07-29 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1320 | Washroom accessories and Partitions Shop Drawings | 2025-07-25 | 2025-07-29 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1610 | Concrete Mix for Hardscapes | 2025-08-04 | 2025-08-06 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1620 | Landscape Shop Drawings | 2025-08-04 | 2025-08-06 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1720 | Millwork | 2025-10-07 | 2025-10-09 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1780 | Hollow Metal Frames | 2025-09-23 | 2025-09-25 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1830 | Aluminum Framed Glazing Systems | 2025-11-26 | 2025-11-28 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1840 | Finished Hardware | 2025-12-03 | 2025-12-05 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1850 | Stud framing & gypsum board | 2025-08-04 | 2025-08-06 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1860 | Tiling | 2025-09-09 | 2025-09-11 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1890 | Flooring | 2025-10-22 | 2025-10-24 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1900 | Paint Drawdowns | 2025-08-11 | 2025-08-13 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1910 | Washroom accessories and Partitions | 2025-09-02 | 2025-09-04 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2200 | Concrete for Hardscape | 2025-08-11 | 2025-08-13 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2210 | Landscape (unit pavers, furniture, etc) | 2025-10-29 | 2025-10-31 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3780 | Layout for Elevator Cylinder | 2025-06-19 | 2025-06-23 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3790 | Drilling Elevator Cylinder from Grade | 2025-06-20 | 2025-06-24 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3800 | Install Steel Casing into the ground | 2025-06-23 | 2025-06-25 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1690 | Structural Reinforcement | 2025-09-16 | 2025-09-18 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it | Yes
A1790 | Hollow Metal Doors | 2025-10-22 | 2025-10-24 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2370 | Bulk Excavation to U/S of Footings | 2025-07-18 | 2025-07-22 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2380 | Bulk Excavation to U/S North Stair Footing | 2025-07-21 | 2025-07-23 | 2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2310 | Relocate FAA | 2025-06-16 | 2025-06-17 | 1 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A3960 | Vinyl Flooring Abatement (Cash Allowance) | 2025-07-14 | 2025-07-11 | -1 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1360 | 23 82 19 - Fan Coil Units (R0) | 2025-07-04 | 2025-07-03 | -1 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1340 | Hydraulic Lift Shop Drawings | 2025-07-11 | 2025-07-09 | -2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1930 | Hydraulic Lift | 2025-12-03 | 2025-12-01 | -2 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A4010 | Underground Plumbing Rough-ins | 2025-07-21 | 2025-07-16 | -3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1380 | 23 21 23 - Pumps (R0) | 2025-07-09 | 2025-07-04 | -3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2390 | Subgrade Inspection | 2025-07-25 | 2025-07-22 | -3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2400 | Subgrade Preparation | 2025-07-28 | 2025-07-23 | -3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2410 | Soil Bearing Capacity Inspection | 2025-07-29 | 2025-07-24 | -3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2430 | Formwork for Pad Footing (GL:AG-AC & X1-A5) | 2025-07-28 | 2025-07-23 | -3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2450 | Rebar for Pad Footings | 2025-07-29 | 2025-07-24 | -3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2460 | Rebar Inspection | 2025-07-30 | 2025-07-25 | -3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2470 | Concrete for Pad Footings (GL:AG-AC & X1-A5) | 2025-07-31 | 2025-07-28 | -3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2490 | Concrete Field Testing | 2025-07-31 | 2025-07-28 | -3 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2040 | 22 13 29 - Sump Pumps | 2025-08-14 | 2025-08-08 | -4 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2360 | Ductbank Shoring | 2025-07-17 | 2025-07-08 | -7 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1600 | 28 31 00 - Fire Alarm Shop Drawings and Data Sheets | 2025-06-26 | 2025-06-17 | -7 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2190 | 28 31 00 - Fire Alarm | 2025-11-05 | 2025-10-27 | -7 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1480 | 23 00 00 - Exhaust Fans (R0) | 2025-08-06 | 2025-07-22 | -11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1490 | 23 00 00 - Unit Heater | 2025-08-06 | 2025-07-22 | -11 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1640 | Foundation Concrete Rebar | 2025-07-04 | 2025-06-13 | -14 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2420 | Form and Pour North Exit Stair | 2025-09-25 | 2025-09-05 | -14 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1630 | Ductbank Underpinning | 2025-06-19 | 2025-05-28 | -16 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A1450 | 22 13 29 - Sump Pumps (R0) | 2025-06-24 | 2025-06-02 | -16 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2480 | Concrete for Remaining Pad Footings (Ramp) | 2025-08-01 | 2025-07-03 | -21 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2080 | 23 00 00 - Unit Heater | 2025-12-12 | 2025-11-11 | -23 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2600 | Compaction Inspection | 2025-09-19 | 2025-08-15 | -24 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it
A2070 | 23 00 00 - Exhaust Fans | 2025-12-12 | 2025-11-03 | -29 | Not attributed | Off the driving envelope; slip recorded, nothing claimed for it

## Activity Register
CPP . CRITICAL PATH PARTNERS |  |  | DWG . CPP-CLM-0001 / SHEET A-90
Cumulative Activity Slip Register
Sum of signed slip across all windows per activity, most-slipped first
PROJECT: Cumulative Activity Slip Register | DATA DATE: 01 Sep 2026 | SHEET: A-90
Activity | Name | Total Slip (d) | Windows Touched | On CP
A4070 | Frames installation | 182 | 1 | Yes
A4060 | Blocking | 169 | 1 | Yes
A4050 | Sprinkler Rough-ins | 162 | 1 | Yes
A4030 | New Partition Framing | 136 | 1 | Yes
A3850 | Foundations | 126 | 1
A3860 | Concrete Vertical Piers | 126 | 1
A3870 | Removal of Existing Facade for Tie In | 126 | 1
A3880 | Structural Steel erection including expansion plates | 94 | 1
A3890 | Envelope | 94 | 1
A4150 | New Exterior Paved Areas and Sidewalks | 94 | 1
A4160 | Landscape Installations | 94 | 1
A3940 | Existing Slab Removal and Trenching | 90 | 1
A3900 | Interior M&E Rough in | 84 | 1
A2090 | 23 52 16 - Heating Boilers | 71 | 1
A3910 | Interior Finishes | 65 | 1
A2730 | Stairs B Installation @ North Side | 62 | 1
A1710 | Misc. Metals | 62 | 1
A2720 | Tactile Attention Indicators Mock-up | 62 | 1
A1500 | 23 52 16 - Heating Boilers | 62 | 1
A1950 | 23 82 19 - Fan Coil Units | 62 | 1
A2050 | 23 25 00 - Water Treatment | 61 | 1
A2060 | 23 37 13 - Diffuser and Grilles | 60 | 1
A3270 | New Stair A Installation | 59 | 1
A2540 | Compaction Inspection | 58 | 1
A2180 | 26 09 23 - Lighting Control | 55 | 1
A3170 | Install Built-up Roof | 54 | 1
A1130 | Misc. Metals Shop Drawings | 53 | 1
A3180 | Roof Inspection | 52 | 1
A1680 | Structural Steel | 48 | 1
A1160 | TPO Roofing Shop Drawings | 47 | 1
A1740 | TPO Roofing (Bridge) | 46 | 1
A1330 | Fall Arrest Anchors and Horizontal Lines | 45 | 1
A2640 | Install Roof Decking | 44 | 1
A2630 | Install Roof Anchors | 44 | 1
A1920 | Fall Arrest Anchors and Horizontal Lines | 44 | 1
A3150 | Roof Parapet Framing | 44 | 1
A3160 | Roof Penetration Layout | 44 | 1
A2510 | Supply of Embedment & Ankors | 44 | 1
A2580 | Underground Drainage | 43 | 1
A2130 | 22 40 00 - Plumbing Fixtures | 42 | 1
A3930 | Interior Demolition | 40 | 1
A2590 | Backfilling to U/S of SOG | 39 | 1
A1970 | 23 21 23 - Pumps | 38 | 1
A1590 | 26 09 23 - Lighting Control (R0) | 36 | 1
A2150 | 26 50 00 - Lighting Fixtures | 35 | 1
A2220 | Testing and Inspection Cash Allowance Expenditure | 34 | 1
A1960 | 23 74 13 - Air Handling Units | 34 | 1
A2440 | Formwork Remaining Pad Footing (Ramp) | 34 | 1
A4040 | MEP Rough-ins | 33 | 1 | Yes
A4080 | Drywall/Sheathing Installation | 33 | 1 | Yes
A4090 | Taping and mudding | 33 | 1 | Yes
A4110 | Tile and Rubber Flooring Installation | 33 | 1 | Yes
A4100 | Painting | 33 | 1 | Yes
A4120 | Final Terminations and Fixtures Installation | 33 | 1 | Yes
A2120 | 20 05 10 - Electric Heat Tracing | 33 | 1
A4170 | Fire Alarm Verification | 32 | 1
A1110 | Structural Reinforcement + Decking Shop Drawings | 30 | 1
A1290 | Suspended Metal Soffits | 28 | 1
A1820 | Coiling Doors | 28 | 1
A1870 | ACT & ACB | 27 | 1
A1460 | 23 25 00 - Water Treatment (R0) | 27 | 1
A1580 | 26 50 00 - Lighting Fixtures | 25 | 1
A1700 | Cold-formed Metal Framing | 24 | 1
A1120 | Cold-formed Metal Framing Shop Drawings | 23 | 1
A1220 | Flush Wood Doors Sample | 23 | 1
A1280 | ACT Data sheet and Sample | 23 | 1
A4240 | Minor Deficiencies & Touch-ups | 22 | 1 | Yes
A1810 | Flush Wood Doors | 22 | 1
A4260 | Total Completion | 21 | 1 | Yes
A4220 | Final Cleaning | 21 | 1
A4180 | Mechanical, Electrical and Elevator Commissioning | 21 | 1 | Yes
A4190 | Integrated Testing | 21 | 1 | Yes
A4250 | Ready-To-Take Over | 21 | 1 | Yes
A4230 | Close-out Documents & Training | 21 | 1
A4210 | Occupancy | 20 | 1 | Yes
A2500 | Install Rebar for Piers | 20 | 1
A4200 | Substantial Performance | 19 | 1 | Yes
A1230 | Coiling Doors | 19 | 1
A1180 | Exterior Wall Cladding Shop Drawings | 18 | 1
A1210 | Interior Aluminum Screen | 18 | 1
A1760 | Exterior Wall Cladding | 18 | 1
A1800 | Interior Aluminum Screens | 17 | 1
A1090 | Masonry and Mortar Samples & Data Sheets | 16 | 1
A1100 | Structural Steel Framing and Steel Deck Shop Drawings (R0) | 16 | 1
A2550 | Form and Pour Grade Beams | 16 | 1
A2560 | Below Grade Vapour Barrier Mock-up | 16 | 1
A2570 | Footing Vapor Barrier & Insulation | 16 | 1
A2750 | L1, L2 & L3 Framing and Sheathing Installation | 15 | 1 | Yes
A2880 | L1, L2 & L3 Framing and Sheathing Installation | 15 | 1 | Yes
A2890 | L1 Masonry Wall Installation | 15 | 1
A2770 | L1 Masonry Wall installation | 15 | 1
A2790 | L1, L2 & L3 Air Vapour Barrier Installation | 15 | 1
A3260 | Seal Concrete Floor | 15 | 1 | Yes
A3430 | Seal concrete Floor | 15 | 1
A3280 | New partition framing | 15 | 1
A3330 | Door frames Installation | 15 | 1
A3440 | New partition framing | 15 | 1
A3560 | Seal concrete Floor | 15 | 1
A1670 | Masonry and Mortar | 15 | 1
A3420 | Fire Spraying & Intumescent Paint | 15 | 1
A3550 | Fire Spraying & Intumescent Paint | 15 | 1
A2820 | Glazing Site Measure and Scanning | 15 | 1
A2280 | Under Pinning Inspection | 15 | 1
A2760 | Masonry Mock-up | 15 | 1
A2740 | Cold-Formed Metal Framing Mock | 15 | 1
A3680 | Misc. Metals Mock-up | 15 | 1
A2780 | Above Grade Vapour Mock-up | 15 | 1
A2800 | AVB Inspection | 15 | 1
A3250 | Fire Spraying & Intumescent Paint Inspection | 15 | 1 | Yes
A2520 | Form and Pour Foundation Piers | 15 | 1
A3490 | Door frames Installation | 14 | 1
A3520 | Door and Hardware Installation | 14 | 1
A3620 | Door frames Installation | 14 | 1
A3570 | New wall partition framing | 14 | 1
A3920 | Setup Temporary Hoarding | 14 | 1
A3240 | Fire Spraying & Intumescent Paint | 14 | 1 | Yes
A3210 | Electrical and Mechanical Room | 14 | 1
A3690 | Misc. Metals installation | 14 | 1
A3220 | Mech. and Elec. Equipment Installation | 14 | 1
A1530 | 20 05 10 - Electric Heat Tracing (R0) | 14 | 1
A2530 | Backfilling to U/S of Grade Beams | 14 | 1
A1060 | Foundation Concrete Rebar Shop Drawing | 12 | 1
A1050 | Ductbank Underpinning Drawing | 12 | 1
A1470 | 23 37 13 - Diffuser and Grilles Shop Drawings (R0) | 12 | 1
A3410 | Painting | 11 | 1
A3300 | Electrical, FA & Comms rough-ins | 11 | 1
A3320 | Blocking Installation | 11 | 1
A3350 | Gypsum board Installation | 11 | 1
A3360 | Drywall Taping and Mudding | 11 | 1
A3390 | Interior Aluminum/Glazing Screens Installation | 11 | 1
A3370 | Door and Hardware Installation | 11 | 1
A3810 | Install Controller at Machine Room | 11 | 1
A3820 | Rails and Elevator Car installation | 11 | 1
A3830 | Power to controller, Phone lines and Comms | 11 | 1
A3840 | Elevator Testing and Commissioning | 11 | 1
A3380 | Interior Aluminum/Glazing Screens Mock-up | 11 | 1
A3340 | ACT Baffles Mock-ups | 11 | 1
A3400 | Paint Mock-up | 11 | 1
A1560 | 26 50 00 - Emergency Lighting & Exit Signs | 11 | 1
A3290 | Mech. & Plumbing rough-ins | 10 | 1
A3310 | Sprinkler Rough-ins | 10 | 1
A3540 | Painting | 9 | 1
A2610 | Erect Structural Steel | 9 | 1
A2650 | Install Level 2 & 3 Decking | 9 | 1
A3450 | Mech. & Plumbing rough-ins | 9 | 1
A3480 | Blocking Installation | 9 | 1
A3500 | Gypsum board Installation | 9 | 1
A3460 | Electrical, FA & Comms rough-ins | 9 | 1
A3510 | Drywall Taping and Mudding | 9 | 1
A3530 | Interior Glazing Installation | 9 | 1
A3590 | Electrical, FA & Comms rough-ins | 9 | 1
A3580 | Mech. & Plumbing rough-ins | 9 | 1
A3610 | Blocking Installation | 9 | 1
A3470 | Sprinkler Rough-ins | 9 | 1
A3600 | Sprinkler Rough-ins | 9 | 1
A2660 | Install Temporary Hoarding for Slab on Deck | 9 | 1
A2620 | Structural Steel Inspection | 9 | 1
A1080 | Bentonite Waterstop Data Sheet | 8 | 1
A1660 | Bentonite Waterstop | 8 | 1
A2140 | 26 27 26 - Wiring Devices, Service Poles, & Floor Boxes | 8 | 1
A1550 | 26 27 26 - Wiring Devices, Service Poles, & Floor Boxes | 7 | 1
A3750 | Washroom Partitions and Accessories Installation | 6 | 1
A2670 | Rebar and Prep Work for Slab on Deck | 6 | 1
A3110 | L1, L2 & L3 Exterior Glazing Installation (W09a, W09b) | 6 | 1
A2930 | L1, L2 & L3 Exterior Glazing Installation (W07a, W07b, W01, W02 & W03) | 6 | 1
A2840 | L1, L2, L3 Exterior Glazing Installation (W05) | 6 | 1
A3010 | L2 & L3 Exterior Glazing Installation (W08a, W08b) | 6 | 1
A3720 | Ceiling/Wall Fixtures Installation | 6 | 1
A3740 | Millwork Installation | 6 | 1
A3710 | Tiling and rubber flooring Installation | 6 | 1
A3670 | Painting | 6 | 1
A3770 | Corner Guards and Wall Protection Installation | 6 | 1
A3660 | Interior Glazing Installation | 6 | 1
A3650 | Door and Hardware Installation | 6 | 1
A3630 | Gypsum board Installation | 6 | 1
A3640 | Drywall Taping and Mudding | 6 | 1
A2850 | Exterior Cladding Site Measure and Scanning | 6 | 1
A2940 | Exterior Cladding Site Measure and Scanning | 6 | 1
A3020 | Exterior Cladding Site Measure and Scanning | 6 | 1
A3100 | Glazing Shop Fabrication | 6 | 1
A3120 | Exterior Cladding Site Measure and Scanning | 6 | 1
A3760 | Plumbing Washroom Fixtures Installation | 6 | 1
A3730 | Millwork Mock-up | 6 | 1
A2810 | Aluminum & Metal Panel Cladding Mock-up | 6 | 1
A3700 | Tiling & Rubber & Carpet Flooring Mock-up | 6 | 1
A1370 | 23 74 13 - Air Handling Units (R0) | 6 | 1
A2030 | 23 81 26 - Split System | 6 | 1
A2160 | 27 10 00 - Structural Cabling System (Fiber Optic Cable) | 6 | 1
A2680 | Concrete pour for slab on deck level 2 & 3 | 5 | 1
A2960 | L2 & L3 Cladding Installation (EW2) | 5 | 1
A2870 | L1, L2 & L3 Cladding Installation (EW2a) | 5 | 1
A3040 | L2 & L3 Cladding Installation (EW2) | 5 | 1
A3050 | Horizontal Shading Louvers | 5 | 1
A2900 | Air Vapor Barrier Installation | 5 | 1
A3140 | L1, L2 & L3 Cladding Installation (EW2, EW2A) | 5 | 1
A3070 | L1, L2 & L3 Air Vapor Barrier Installation | 5 | 1
A2690 | Final Grading and Vapor Barrier for SOG | 5 | 1
A2860 | Exterior Cladding Shop Fabrication | 5 | 1
A2910 | Glazing Site Measure and Scanning | 5 | 1
A2950 | Exterior Cladding Shop Fabrication | 5 | 1
A3000 | Glazing Shop Fabrication | 5 | 1
A3030 | Exterior Cladding Shop Fabrication | 5 | 1
A3130 | Exterior Cladding Shop Fabrication | 5 | 1
A3080 | L1, L2 & L3 Air Vapor Barrier Inspection | 5 | 1
A1420 | 23 57 00 - Heat Exchangers | 5 | 1
A1570 | 27 10 00 - Structural Cabling System (Fiber Optic Cable) | 5 | 1
A2970 | L2 & L3 Framing and Sheathing Installation | 4 | 1 | Yes
A3060 | L1, L2 & L3 Framing and Sheathing Installation | 4 | 1 | Yes
A2980 | L2 & L3 Air Vapor Barrier Installation | 4 | 1
A1070 | Foundation Concrete Mix Design | 4 | 1
A1650 | Foundation Concrete Mix Design | 4 | 1
A2830 | Glazing Shop Fabrication | 4 | 1
A2920 | Glazing Shop Fabrication | 4 | 1
A2990 | Glazing Site Measure and Scanning | 4 | 1
A3090 | Glazing Site Measure and Scanning | 4 | 1
A3230 | Fire Spraying & Intumescent Paint Mock-up | 4 | 1
A1510 | 23 00 00 - Wall Fin Heater | 4 | 1
A1540 | 22 40 00 - Plumbing Fixtures (R0) | 4 | 1
A2100 | 23 00 00 - Wall Fin Heater | 4 | 1
A1040 | Permit (Not Required Per Ontario Community College) | 3 | 1
A1030 | IFC Drawings Released | 3 | 1
A1150 | Built-up Roofing Shop Drawings | 3 | 1
A1170 | Air Barrier System Data Sheet and Mockup | 3 | 1
A1190 | Fire-resistive Material Data Sheet | 3 | 1
A1350 | Sprinkler & Standpipe Shop Drawings | 3 | 1
A1730 | Built-up Roofing | 3 | 1
A1750 | Air Barrier System | 3 | 1
A1770 | Fire-resistive Material | 3 | 1
A1940 | Sprinkler & Standpipe Shop Drawings | 3 | 1
A2710 | Concrete Pour and Curing for SOG | 3 | 1
A2700 | Rebar Installation for SOG | 3 | 1
A3190 | Hoisting Roof Equipment | 3 | 1
A3200 | Roof Anchor System Installation | 3 | 1
A1390 | 23 25 00 - Buffer Tanks | 3 | 1
A1400 | 23 21 16 - Air Separator | 3 | 1
A1410 | 23 21 16 - Expansion Tanks | 3 | 1
A1520 | 23 74 13 - Air Source Heat Pump | 3 | 1
A2110 | 23 74 13 - Air Source Heat Pump | 3 | 1
A2240 | Construction Site Setup. Fencing and Temp Facilities | 2 | 1
A1010 | Contract Award | 2 | 1
A2230 | Ontario Community College Auto Show | 2 | 1
A2270 | Excavation for Under Pinning | 2 | 1
A2250 | Tree Removal, Protection and Equipment Mobilization | 2 | 1
A2260 | Top Soil Stripping | 2 | 1
A2300 | Setup Hoarding @ Vestibule F100 | 2 | 1
A2320 | Demolition of Existing Vestibule F100 | 2 | 1
A2290 | Existing Structure Under Pinning | 2 | 1
A2330 | Gas Meter and Pipe Relocation Investigation | 2 | 1
A2340 | Gas Meter and pipe Relocation | 2 | 1
A2350 | Daylighting of Existing Hydro Ductbank & Services | 2 | 1
A1020 | Subcontract Award | 2 | 1
A1140 | Millwork Shop Drawings | 2 | 1
A1200 | Hollow Metal Frames & Doors Shop Drawings | 2 | 1
A1240 | Aluminum Framed Glazing System Shop Drawings | 2 | 1
A1250 | Finished Hardware Schedule | 2 | 1
A1260 | Stud framing and Gypsum Board Data Sheets | 2 | 1
A1270 | Tiling Data sheet and samples | 2 | 1
A1300 | Flooring Data Sheets and Samples | 2 | 1
A1310 | Paint Drawdowns | 2 | 1
A1320 | Washroom accessories and Partitions Shop Drawings | 2 | 1
A1610 | Concrete Mix for Hardscapes | 2 | 1
A1620 | Landscape Shop Drawings | 2 | 1
A1720 | Millwork | 2 | 1
A1780 | Hollow Metal Frames | 2 | 1
A1830 | Aluminum Framed Glazing Systems | 2 | 1
A1840 | Finished Hardware | 2 | 1
A1850 | Stud framing & gypsum board | 2 | 1
A1860 | Tiling | 2 | 1
A1890 | Flooring | 2 | 1
A1900 | Paint Drawdowns | 2 | 1
A1910 | Washroom accessories and Partitions | 2 | 1
A2200 | Concrete for Hardscape | 2 | 1
A2210 | Landscape (unit pavers, furniture, etc) | 2 | 1
A3780 | Layout for Elevator Cylinder | 2 | 1
A3790 | Drilling Elevator Cylinder from Grade | 2 | 1
A3800 | Install Steel Casing into the ground | 2 | 1
A1690 | Structural Reinforcement | 2 | 1 | Yes
A1790 | Hollow Metal Doors | 2 | 1
A2370 | Bulk Excavation to U/S of Footings | 2 | 1
A2380 | Bulk Excavation to U/S North Stair Footing | 2 | 1
A2310 | Relocate FAA | 1 | 1
A3960 | Vinyl Flooring Abatement (Cash Allowance) | -1 | 1
A1360 | 23 82 19 - Fan Coil Units (R0) | -1 | 1
A1340 | Hydraulic Lift Shop Drawings | -2 | 1
A1930 | Hydraulic Lift | -2 | 1
A4010 | Underground Plumbing Rough-ins | -3 | 1
A1380 | 23 21 23 - Pumps (R0) | -3 | 1
A2390 | Subgrade Inspection | -3 | 1
A2400 | Subgrade Preparation | -3 | 1
A2410 | Soil Bearing Capacity Inspection | -3 | 1
A2430 | Formwork for Pad Footing (GL:AG-AC & X1-A5) | -3 | 1
A2450 | Rebar for Pad Footings | -3 | 1
A2460 | Rebar Inspection | -3 | 1
A2470 | Concrete for Pad Footings (GL:AG-AC & X1-A5) | -3 | 1
A2490 | Concrete Field Testing | -3 | 1
A2040 | 22 13 29 - Sump Pumps | -4 | 1
A2360 | Ductbank Shoring | -7 | 1
A1600 | 28 31 00 - Fire Alarm Shop Drawings and Data Sheets | -7 | 1
A2190 | 28 31 00 - Fire Alarm | -7 | 1
A1480 | 23 00 00 - Exhaust Fans (R0) | -11 | 1
A1490 | 23 00 00 - Unit Heater | -11 | 1
A1640 | Foundation Concrete Rebar | -14 | 1
A2420 | Form and Pour North Exit Stair | -14 | 1
A1630 | Ductbank Underpinning | -16 | 1
A1450 | 22 13 29 - Sump Pumps (R0) | -16 | 1
A2480 | Concrete for Remaining Pad Footings (Ramp) | -21 | 1
A2080 | 23 00 00 - Unit Heater | -23 | 1
A2600 | Compaction Inspection | -24 | 1
A2070 | 23 00 00 - Exhaust Fans | -29 | 1
All 309 activities listed, never truncated. Total Slip is the signed sum across every analysis window.

## Entitlement Calculation
CPP . CRITICAL PATH PARTNERS |  |  |  | DWG . CPP-CLM-0001 / SHEET A-99
Entitlement Calculation
Net working-day entitlement per delay event
PROJECT: Entitlement Calculation |  | DATA DATE: 01 Sep 2026 |  | SHEET: A-99
Exhibit | Event | Gross WD | Concurrent WD | Net WD | Notes
DE-01 | Fire-spray application held for owner inspector availability | 9 | 0 | 9 | No concurrent delay is claimed for this event. Contractor-caused slip in the same window (12 working days on remobilization, trade stacking and deficiency re-work) is attributed to the contractor in the windows analysis and is not claimed.
— | TOTAL |  |  | 9 | Gross/Concurrent not summed (would double-count concurrency).
Net WD claimed (sum) 9d . All 1 delay events listed, never truncated. . Engine cpm-engine v2.9.42 |  |  |  |  | Reproducible . Engineered for Daubert scrutiny