| CPP Critical Path Partners Forensic schedule analysis | FDA-01 |
| --- | --- |

| Cedarline Pump Station Retrofit Windows Analysis · AACE MIP 3.3 Windows 3 Period 03-Feb-2025 to 30-Sep-2025 Generated 08-Oct-2026 | Overall +17 wd |
| --- | --- |

| Field | Value |
| --- | --- |
| Project | Cedarline Pump Station Retrofit |
| Analysis windows | 3 |
| Period covered | Baseline to Update 3 |
| Entitlement milestone | MS-SC |
| Prepared by | Dana Fitkowski |
| Firm | Critical Path Partners |
| Date prepared | 8 October 2026 |

A-00   Summary of delay findings

Completion moved from 11 September 2025 to 6 October 2025, 17 working days later than the baseline. None of that movement is attributed to a party; 17 working days remain unattributed.

| No. | Data dates | Shift | Owner wd | Contractor wd | Other wd | Drivers on the driving path |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 03-Feb-2025 to 31-Mar-2025 | +8 wd | 0 | 0 | 8 | CIV-BASE (own growth, 8 wd) |
| 2 | 31-Mar-2025 to 30-Jun-2025 | +7 wd | 0 | 0 | 7 | nothing on the driving path moved |
| 3 | 30-Jun-2025 to 30-Sep-2025 | +2 wd | 0 | 0 | 2 | nothing on the driving path moved |

A-01   Executive Summary

| Baseline to Final Slip +17 wd completion against baseline (working days) | Window Shifts +17 wd sum of per-window shifts (working days) | Analysis Windows 3 schedule update windows | Unattributed 17 wd slip awaiting a responsible party |
| --- | --- | --- | --- |

The project has slipped 17 working days from baseline completion to the latest projection. Across 3 analysis windows, the window-by-window shift sums to 17 working days. 17 slip-days remain unattributed in the slip register; these must be assigned a responsible party before the entitlement position is final.

Attribution work is incomplete. Once the responsible-party column on each slip register entry is filled in, the position by party can be stated.

A-01.2   Basis of measurement

| Convention | As applied in this report |
| --- | --- |
| Day unit | Working days. Every day count in this deliverable is in working days. No calendar-day figure is displayed. Where a contract clause is quoted verbatim in calendar days, the computed equivalent is given in working days alongside. |
| Calendar | The activity's own P6 calendar. Deltas are counted on the activity's own P6 calendar via work_day_delta. Where no project calendar is available the documented fallback is Monday to Friday with no holidays, and that fallback is disclosed on the affected figure. |
| Date fields read | P6 Start and Finish columns only |

A positive figure means the date moved later between the earlier and the later schedule, which is the adverse direction in this report. Convention: forensic-slip: positive = the date moved later between the two schedules compared. One uniform subtraction order is used, later schedule minus earlier schedule, so a negative figure means the date moved earlier and is a recovery. This is the reverse of the contractor-loss convention used in the contract-versus-baseline deliverables; the two must not be read against each other without converting the sign.

| Variance | How it is computed | A positive value means |
| --- | --- | --- |
| Completion shift | completion at the later data date - completion at the earlier data date | completion moved later, slip |
| Activity slip | activity finish in the later schedule - activity finish in the earlier schedule | the activity finishes later, slip |

A-02   Methodology

Prepared in accordance with AACE International Recommended Practice 29R-03: Forensic Schedule Analysis. This report follows MIP 3.3 (Observational / Dynamic / Contemporaneous As-Is, Windows Analysis): each sequential schedule update establishes a discrete analysis window; project delay is measured by the movement of the forecasted completion date window-over-window and attributed to the delay drivers evident within that window.

This analysis applies a windows-based as-planned-versus-as-built methodology over 3 schedule update windows. Each window compares the prior XER snapshot to the later snapshot and identifies: (1) shifts in the projected completion date, (2) duration growth on critical-path activities, (3) changes in critical-path membership, (4) logic changes (added, removed, retyped or relagged relationships), (5) added or removed activities, and (6) every activity whose finish date moved between snapshots. Date math uses each activity's assigned P6 calendar where available.

Critical activities are those with total float of zero or less, except in a schedule with negative float, where they are the unfinished activities on the driving path. The driving path is the set of chains of driving relationships into the schedule's forecast finish, traced on the schedule's own dates to the working day with every tied chain included, so it does not depend on P6's Longest Path flag.

A-02.1   Authorities and Precedents

The methodology and analytical conclusions in this report rely on the following authorities. Each citation is referenced where its doctrine governs an attribution, apportionment, damages, or admissibility decision.

| Authority | Citation | Doctrine |
| --- | --- | --- |
| AACE 67R-11 | AACE International Recommended Practice 67R-11 "Contract Risk Allocation, Differing Site Conditions for EPC Projects" | Risk allocation + float ownership |
| SCL Protocol 2nd Ed. | Society of Construction Law Delay and Disruption Protocol, 2nd Edition (Feb 2017) | Delay analysis + concurrent delay |
| FRE 702 (Dec 2023 amendment) | Federal Rule of Evidence 702 (as amended effective December 1, 2023): expert testimony admissible only if the proponent demonstrates to the court that it is "more likely than not" that the testimony is based on sufficient facts/data, is the product of reliable principles and methods, and "reflects a reliable application of the principles and methods to the facts of the case." | Daubert gatekeeping, expert admissibility burden |
| AACE PPG #20 (2nd Ed.) | AACE International Professional Practice Guide #20 "Forensic Schedule Analysis," 2nd Edition (2024), Roger Nelson PE PSP & Steve Purugganan eds., companion to RP 29R-03; collected case-study commentary applying the MIPs in practice. | Forensic schedule analysis, applied case studies |
| Jones (Secretariat 2025) | Stuart Jones, "Overtaken by Events: What Delay Quantification Can Tell Us About Causality," International Construction Law Review (Aug 19, 2025), two-stage framework separating objective network quantification from legal/contractual causation; acknowledges epistemic limits of as-planned vs as-built when intervening events overtake the baseline's presumed sequence. | Causation limit doctrine, windows analysis context |
| Malmaison | Henry Boot Construction (UK) Ltd v Malmaison Hotel (Manchester) Ltd (1999) 70 Con LR 32 (TCC, Dyson J) | Concurrent delay, Malmaison principle |

A-03   Window-by-Window Analysis

A-03.1   Window 1: Baseline → Update 1

| Completion Shift +8 wd this window (working days) | Cumulative against Baseline +8 wd running total (working days) |
| --- | --- |

Period: 3 February 2025 to 31 March 2025. Completion date shift this window: 8 working days. Cumulative shift against baseline: 8 working days.

Completion-shift basis. The window shift above is measured on the finish driver, not on the PROJECT scheduled finish (which is cross-checked only).

| Field | Value |
| --- | --- |
| Shift basis | Latest activity finish |
| Finish activity | COM-DEMOB |
| Date field used | early_end_date |
| Scheduled finish (prior) | 11-Sep-2025 |
| Scheduled finish (later) | 23-Sep-2025 |
| Basis vs project finish | Consistent |

Critical path membership changes. Newly critical: none. No longer critical: CIV-EXC, CIV-MUD, MS-NTP, PRE-PERMIT.

A-03.1a   Critical-Path Duration Changes

1 critical-path activity changed scheduler-estimated duration: 1 grew, 0 reduced. Each day of growth on a CP activity is direct delay to the project completion; a reduction recovers time.

| Code | Activity | Prior Duration | Later Duration | Change |
| --- | --- | --- | --- | --- |
| CIV-BASE | Form Reinforce and Pour Base Slab | 12 wd | 20 wd | +8 wd |

A-03.1b   Slip Register

26 activities moved their finish date in this window. Each entry requires attribution to a responsible party.

Warn [FILL IN: 26 of 26 slip register entries in this window lack a responsible_party assignment. Fill in the dashboard slip-register or the source data dict before finalising this report.]

| Code | Activity | Prior Finish | Later Finish | Slip | Responsible | On CP |
| --- | --- | --- | --- | --- | --- | --- |
| ELE-PROC | MCC and VFD Fabrication and Delivery | 24-Mar-2025 | 09-Apr-2025 | +12 wd |  |  |
| CIV-BASE | Form Reinforce and Pour Base Slab | 08-Apr-2025 | 21-Apr-2025 | +8 wd |  | Yes |
| CIV-WALL | Form Reinforce and Pour Wet Well Walls | 29-Apr-2025 | 09-May-2025 | +8 wd |  | Yes |
| CIV-CURE | Wall Cure and Strip Formwork | 08-May-2025 | 21-May-2025 | +8 wd |  | Yes |
| MS-CONC | Concrete Structure Complete | 08-May-2025 | 21-May-2025 | +8 wd |  | Yes |
| CIV-BKF | Backfill and Compact Around Structure | 16-May-2025 | 29-May-2025 | +8 wd |  |  |
| CIV-SLAB | Grade Slab and Equipment Pads | 29-May-2025 | 10-Jun-2025 | +8 wd |  |  |
| MEC-SET | Set Pump Skids and Grout Baseplates | 21-May-2025 | 02-Jun-2025 | +8 wd |  |  |
| MEC-PIPE | Internal Process Piping Install | 16-Jun-2025 | 26-Jun-2025 | +8 wd |  |  |
| MEC-VALVE | Valve and Actuator Install | 24-Jun-2025 | 07-Jul-2025 | +8 wd |  |  |
| MEC-TEST | Hydrostatic Test Process Piping | 02-Jul-2025 | 14-Jul-2025 | +8 wd |  |  |
| ELE-COND | Conduit and Cable Tray Rough-In | 20-Jun-2025 | 03-Jul-2025 | +8 wd |  | Yes |
| ELE-MCC | Set MCC and VFD Line-Up | 27-Jun-2025 | 10-Jul-2025 | +8 wd |  | Yes |
| ELE-CABLE | Power and Control Cable Pull | 16-Jul-2025 | 28-Jul-2025 | +8 wd |  | Yes |
| ELE-TERM | Terminate and Point-to-Point Check | 28-Jul-2025 | 08-Aug-2025 | +8 wd |  | Yes |
| MS-ENERG | Permanent Power Energized | 28-Jul-2025 | 08-Aug-2025 | +8 wd |  | Yes |
| BLD-ERECT | Erect Pre-Engineered Building Frame | 23-May-2025 | 04-Jun-2025 | +8 wd |  | Yes |
| BLD-ROOF | Roof Deck and Membrane | 02-Jun-2025 | 12-Jun-2025 | +8 wd |  | Yes |
| BLD-CLAD | Wall Cladding and Flashing | 12-Jun-2025 | 24-Jun-2025 | +8 wd |  |  |
| BLD-DOOR | Overhead Doors and Louvres | 18-Jun-2025 | 30-Jun-2025 | +8 wd |  |  |
| COM-FLUSH | System Flush and Chlorination | 05-Aug-2025 | 15-Aug-2025 | +8 wd |  | Yes |
| COM-LOOP | Instrument Loop Checks | 15-Aug-2025 | 27-Aug-2025 | +8 wd |  | Yes |
| COM-FUNC | Functional Testing All Modes | 29-Aug-2025 | 11-Sep-2025 | +8 wd |  | Yes |
| COM-PERF | Performance and Capacity Demonstration | 08-Sep-2025 | 18-Sep-2025 | +8 wd |  | Yes |
| COM-DEMOB | Demobilize and Turnover Documentation | 11-Sep-2025 | 23-Sep-2025 | +8 wd |  | Yes |
| MS-SC | Substantial Completion | 11-Sep-2025 | 23-Sep-2025 | +8 wd |  | Yes |

Warn [FILL IN: Provide a chronological narrative of what drove this window's slip. Reference specific activity codes, dates, RFIs, change orders, weather events, or other cause documents. This is the prose that turns the data above into a claim story.]

A-03.2   Window 2: Update 1 → Update 2

| Completion Shift +7 wd this window (working days) | Cumulative against Baseline +15 wd running total (working days) |
| --- | --- |

Period: 31 March 2025 to 30 June 2025. Completion date shift this window: 7 working days. Cumulative shift against baseline: 15 working days.

Completion-shift basis. The window shift above is measured on the finish driver, not on the PROJECT scheduled finish (which is cross-checked only).

| Field | Value |
| --- | --- |
| Shift basis | Latest activity finish |
| Finish activity | COM-DEMOB |
| Date field used | early_end_date |
| Scheduled finish (prior) | 23-Sep-2025 |
| Scheduled finish (later) | 02-Oct-2025 |
| Basis vs project finish | Consistent |

Critical path membership changes. Newly critical: none. No longer critical: BLD-ERECT, BLD-ROOF, CIV-BASE, CIV-CURE, CIV-WALL, MS-CONC.

A-03.2b   Slip Register

24 activities moved their finish date in this window. Each entry requires attribution to a responsible party.

Warn [FILL IN: 24 of 24 slip register entries in this window lack a responsible_party assignment. Fill in the dashboard slip-register or the source data dict before finalising this report.]

| Code | Activity | Prior Finish | Later Finish | Slip | Responsible | On CP |
| --- | --- | --- | --- | --- | --- | --- |
| CIV-WALL | Form Reinforce and Pour Wet Well Walls | 09-May-2025 | 21-May-2025 | +7 wd |  |  |
| CIV-CURE | Wall Cure and Strip Formwork | 21-May-2025 | 30-May-2025 | +7 wd |  |  |
| MS-CONC | Concrete Structure Complete | 21-May-2025 | 30-May-2025 | +7 wd |  |  |
| CIV-BKF | Backfill and Compact Around Structure | 29-May-2025 | 09-Jun-2025 | +7 wd |  |  |
| CIV-SLAB | Grade Slab and Equipment Pads | 10-Jun-2025 | 19-Jun-2025 | +7 wd |  |  |
| MEC-SET | Set Pump Skids and Grout Baseplates | 02-Jun-2025 | 11-Jun-2025 | +7 wd |  |  |
| MEC-PIPE | Internal Process Piping Install | 26-Jun-2025 | 08-Jul-2025 | +7 wd |  |  |
| MEC-VALVE | Valve and Actuator Install | 07-Jul-2025 | 16-Jul-2025 | +7 wd |  |  |
| MEC-TEST | Hydrostatic Test Process Piping | 14-Jul-2025 | 23-Jul-2025 | +7 wd |  |  |
| ELE-COND | Conduit and Cable Tray Rough-In | 03-Jul-2025 | 14-Jul-2025 | +7 wd |  | Yes |
| ELE-MCC | Set MCC and VFD Line-Up | 10-Jul-2025 | 21-Jul-2025 | +7 wd |  | Yes |
| ELE-CABLE | Power and Control Cable Pull | 28-Jul-2025 | 07-Aug-2025 | +7 wd |  | Yes |
| ELE-TERM | Terminate and Point-to-Point Check | 08-Aug-2025 | 19-Aug-2025 | +7 wd |  | Yes |
| MS-ENERG | Permanent Power Energized | 08-Aug-2025 | 19-Aug-2025 | +7 wd |  | Yes |
| BLD-ERECT | Erect Pre-Engineered Building Frame | 04-Jun-2025 | 13-Jun-2025 | +7 wd |  |  |
| BLD-ROOF | Roof Deck and Membrane | 12-Jun-2025 | 23-Jun-2025 | +7 wd |  |  |
| BLD-CLAD | Wall Cladding and Flashing | 24-Jun-2025 | 04-Jul-2025 | +7 wd |  |  |
| BLD-DOOR | Overhead Doors and Louvres | 30-Jun-2025 | 10-Jul-2025 | +7 wd |  |  |
| COM-FLUSH | System Flush and Chlorination | 15-Aug-2025 | 26-Aug-2025 | +7 wd |  | Yes |
| COM-LOOP | Instrument Loop Checks | 27-Aug-2025 | 08-Sep-2025 | +7 wd |  | Yes |
| COM-FUNC | Functional Testing All Modes | 11-Sep-2025 | 22-Sep-2025 | +7 wd |  | Yes |
| COM-PERF | Performance and Capacity Demonstration | 18-Sep-2025 | 29-Sep-2025 | +7 wd |  | Yes |
| COM-DEMOB | Demobilize and Turnover Documentation | 23-Sep-2025 | 02-Oct-2025 | +7 wd |  | Yes |
| MS-SC | Substantial Completion | 23-Sep-2025 | 02-Oct-2025 | +7 wd |  | Yes |

Warn [FILL IN: Provide a chronological narrative of what drove this window's slip. Reference specific activity codes, dates, RFIs, change orders, weather events, or other cause documents. This is the prose that turns the data above into a claim story.]

A-03.3   Window 3: Update 2 → Update 3

| Completion Shift +2 wd this window (working days) | Cumulative against Baseline +17 wd running total (working days) |
| --- | --- |

Period: 30 June 2025 to 30 September 2025. Completion date shift this window: 2 working days. Cumulative shift against baseline: 17 working days.

Completion-shift basis. The window shift above is measured on the finish driver, not on the PROJECT scheduled finish (which is cross-checked only).

| Field | Value |
| --- | --- |
| Shift basis | Latest activity finish |
| Finish activity | COM-DEMOB |
| Date field used | early_end_date |
| Scheduled finish (prior) | 02-Oct-2025 |
| Scheduled finish (later) | 06-Oct-2025 |
| Basis vs project finish | Consistent |

Critical path membership changes. Newly critical: none. No longer critical: COM-FLUSH, COM-FUNC, COM-LOOP, ELE-CABLE, ELE-COND, ELE-MCC, ELE-TERM, MS-ENERG.

A-03.3b   Slip Register

14 activities moved their finish date in this window. Each entry requires attribution to a responsible party.

Warn [FILL IN: 14 of 14 slip register entries in this window lack a responsible_party assignment. Fill in the dashboard slip-register or the source data dict before finalising this report.]

| Code | Activity | Prior Finish | Later Finish | Slip | Responsible | On CP |
| --- | --- | --- | --- | --- | --- | --- |
| MEC-PIPE | Internal Process Piping Install | 08-Jul-2025 | 16-Jul-2025 | +6 wd |  |  |
| MEC-VALVE | Valve and Actuator Install | 16-Jul-2025 | 24-Jul-2025 | +6 wd |  |  |
| MEC-TEST | Hydrostatic Test Process Piping | 23-Jul-2025 | 31-Jul-2025 | +6 wd |  |  |
| ELE-COND | Conduit and Cable Tray Rough-In | 14-Jul-2025 | 22-Jul-2025 | +6 wd |  |  |
| ELE-MCC | Set MCC and VFD Line-Up | 21-Jul-2025 | 29-Jul-2025 | +6 wd |  |  |
| ELE-CABLE | Power and Control Cable Pull | 07-Aug-2025 | 15-Aug-2025 | +6 wd |  |  |
| ELE-TERM | Terminate and Point-to-Point Check | 19-Aug-2025 | 27-Aug-2025 | +6 wd |  |  |
| MS-ENERG | Permanent Power Energized | 19-Aug-2025 | 27-Aug-2025 | +6 wd |  |  |
| COM-FLUSH | System Flush and Chlorination | 26-Aug-2025 | 04-Sep-2025 | +6 wd |  |  |
| COM-LOOP | Instrument Loop Checks | 08-Sep-2025 | 16-Sep-2025 | +6 wd |  |  |
| COM-FUNC | Functional Testing All Modes | 22-Sep-2025 | 24-Sep-2025 | +2 wd |  |  |
| COM-PERF | Performance and Capacity Demonstration | 29-Sep-2025 | 01-Oct-2025 | +2 wd |  | Yes |
| COM-DEMOB | Demobilize and Turnover Documentation | 02-Oct-2025 | 06-Oct-2025 | +2 wd |  | Yes |
| MS-SC | Substantial Completion | 02-Oct-2025 | 06-Oct-2025 | +2 wd |  | Yes |

Warn [FILL IN: Provide a chronological narrative of what drove this window's slip. Reference specific activity codes, dates, RFIs, change orders, weather events, or other cause documents. This is the prose that turns the data above into a claim story.]

A-04   Delay Drivers, Aggregated

| Delay Drivers 64 across 3 windows | On Critical Path 31 48.4% of drivers |
| --- | --- |

64 activity-level delay drivers across 3 windows. 31 (48.4%) were on the critical path at the time of the shift.

A-04.1   Driver Type Breakdown

| Driver Type | Count | % of Total |
| --- | --- | --- |
| Critical Slip | 30 | 46.9% |
| Near-Critical Slip | 18 | 28.1% |
| Activity Slip | 11 | 17.2% |
| Duration Growth | 4 | 6.2% |
| Duration Growth (CP) | 1 | 1.6% |

A-04.2   Delay Drivers, Ranked by Slip Magnitude

All 64 drivers are listed below (full register), ranked by absolute slip magnitude. Delay_Drivers.csv carries the same data in machine-readable form.

| Code | Activity | Type | Slip (wd) | Duration change (wd) | On CP | TF before (wd) | TF after (wd) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ELE-PROC | MCC and VFD Fabrication and Delivery | Duration Growth | 12 | 12 | No | 62 | 58 |
| CIV-BASE | Form Reinforce and Pour Base Slab | Duration Growth (CP) | 8 | 8 | Yes | 0 | 0 |
| CIV-WALL | Form Reinforce and Pour Wet Well Walls | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| CIV-CURE | Wall Cure and Strip Formwork | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| MS-CONC | Concrete Structure Complete | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| CIV-BKF | Backfill and Compact Around Structure | Near-Critical Slip | 8 | 0 | No | 2 | 2 |
| CIV-SLAB | Grade Slab and Equipment Pads | Near-Critical Slip | 8 | 0 | No | 2 | 2 |
| MEC-SET | Set Pump Skids and Grout Baseplates | Activity Slip | 8 | 0 | No | 18 | 18 |
| MEC-PIPE | Internal Process Piping Install | Activity Slip | 8 | 0 | No | 18 | 18 |
| MEC-VALVE | Valve and Actuator Install | Activity Slip | 8 | 0 | No | 18 | 18 |
| MEC-TEST | Hydrostatic Test Process Piping | Activity Slip | 8 | 0 | No | 18 | 18 |
| ELE-COND | Conduit and Cable Tray Rough-In | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| ELE-MCC | Set MCC and VFD Line-Up | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| ELE-CABLE | Power and Control Cable Pull | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| ELE-TERM | Terminate and Point-to-Point Check | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| MS-ENERG | Permanent Power Energized | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| BLD-ERECT | Erect Pre-Engineered Building Frame | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| BLD-ROOF | Roof Deck and Membrane | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| BLD-CLAD | Wall Cladding and Flashing | Activity Slip | 8 | 0 | No | 58 | 58 |
| BLD-DOOR | Overhead Doors and Louvres | Activity Slip | 8 | 0 | No | 58 | 58 |
| COM-FLUSH | System Flush and Chlorination | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| COM-LOOP | Instrument Loop Checks | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| COM-FUNC | Functional Testing All Modes | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| COM-PERF | Performance and Capacity Demonstration | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| COM-DEMOB | Demobilize and Turnover Documentation | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| MS-SC | Substantial Completion | Critical Slip | 8 | 0 | Yes | 0 | 0 |
| CIV-WALL | Form Reinforce and Pour Wet Well Walls | Duration Growth | 7 | 7 | No | 0 | 0 |
| CIV-CURE | Wall Cure and Strip Formwork | Near-Critical Slip | 7 | 0 | No | 0 | 0 |
| MS-CONC | Concrete Structure Complete | Near-Critical Slip | 7 | 0 | No | 0 | 0 |
| CIV-BKF | Backfill and Compact Around Structure | Near-Critical Slip | 7 | 0 | No | 2 | 0 |
| CIV-SLAB | Grade Slab and Equipment Pads | Near-Critical Slip | 7 | 0 | No | 2 | 0 |
| MEC-SET | Set Pump Skids and Grout Baseplates | Near-Critical Slip | 7 | 0 | No | 18 | 0 |
| MEC-PIPE | Internal Process Piping Install | Activity Slip | 7 | 0 | No | 18 | 18 |
| MEC-VALVE | Valve and Actuator Install | Activity Slip | 7 | 0 | No | 18 | 18 |
| MEC-TEST | Hydrostatic Test Process Piping | Activity Slip | 7 | 0 | No | 18 | 18 |
| ELE-COND | Conduit and Cable Tray Rough-In | Critical Slip | 7 | 0 | Yes | 0 | 0 |
| ELE-MCC | Set MCC and VFD Line-Up | Critical Slip | 7 | 0 | Yes | 0 | 0 |
| ELE-CABLE | Power and Control Cable Pull | Critical Slip | 7 | 0 | Yes | 0 | 0 |
| ELE-TERM | Terminate and Point-to-Point Check | Critical Slip | 7 | 0 | Yes | 0 | 0 |
| MS-ENERG | Permanent Power Energized | Critical Slip | 7 | 0 | Yes | 0 | 0 |
| BLD-ERECT | Erect Pre-Engineered Building Frame | Near-Critical Slip | 7 | 0 | No | 0 | 0 |
| BLD-ROOF | Roof Deck and Membrane | Near-Critical Slip | 7 | 0 | No | 0 | 0 |
| BLD-CLAD | Wall Cladding and Flashing | Activity Slip | 7 | 0 | No | 58 | 58 |
| BLD-DOOR | Overhead Doors and Louvres | Activity Slip | 7 | 0 | No | 58 | 58 |
| COM-FLUSH | System Flush and Chlorination | Critical Slip | 7 | 0 | Yes | 0 | 0 |
| COM-LOOP | Instrument Loop Checks | Critical Slip | 7 | 0 | Yes | 0 | 0 |
| COM-FUNC | Functional Testing All Modes | Critical Slip | 7 | 0 | Yes | 0 | 0 |
| COM-PERF | Performance and Capacity Demonstration | Critical Slip | 7 | 0 | Yes | 0 | 0 |
| COM-DEMOB | Demobilize and Turnover Documentation | Critical Slip | 7 | 0 | Yes | 0 | 0 |
| MS-SC | Substantial Completion | Critical Slip | 7 | 0 | Yes | 0 | 0 |
| MEC-PIPE | Internal Process Piping Install | Duration Growth | 6 | 6 | No | 18 | 0 |
| MEC-VALVE | Valve and Actuator Install | Near-Critical Slip | 6 | 0 | No | 18 | 0 |
| MEC-TEST | Hydrostatic Test Process Piping | Near-Critical Slip | 6 | 0 | No | 18 | 0 |
| ELE-COND | Conduit and Cable Tray Rough-In | Duration Growth | 6 | 6 | No | 0 | 0 |
| ELE-MCC | Set MCC and VFD Line-Up | Near-Critical Slip | 6 | 0 | No | 0 | 0 |
| ELE-CABLE | Power and Control Cable Pull | Near-Critical Slip | 6 | 0 | No | 0 | 0 |
| ELE-TERM | Terminate and Point-to-Point Check | Near-Critical Slip | 6 | 0 | No | 0 | 0 |
| MS-ENERG | Permanent Power Energized | Near-Critical Slip | 6 | 0 | No | 0 | 0 |
| COM-FLUSH | System Flush and Chlorination | Near-Critical Slip | 6 | 0 | No | 0 | 0 |
| COM-LOOP | Instrument Loop Checks | Near-Critical Slip | 6 | 0 | No | 0 | 0 |
| COM-FUNC | Functional Testing All Modes | Near-Critical Slip | 2 | -4 | No | 0 | 0 |
| COM-PERF | Performance and Capacity Demonstration | Critical Slip | 2 | 0 | Yes | 0 | 0 |
| COM-DEMOB | Demobilize and Turnover Documentation | Critical Slip | 2 | 0 | Yes | 0 | 0 |
| MS-SC | Substantial Completion | Critical Slip | 2 | 0 | Yes | 0 | 0 |

A-05   Float Burndown Across Windows

| Activities Tracked 23 critical and near-critical, all listed | Crossed TF 0 21 burned to zero float | Recovery Events 0 TF increase observed | Snapshots 4 CPM snapshots |
| --- | --- | --- | --- |

Per-activity total-float erosion timeline for all 23 critical and near-critical activities (every activity at or below 5 working days total float in at least one of 4 snapshots, ordered by minimum TF). This is the complete critical and near-critical set, not a top-N subset. It answers which activities burned float to zero, when they crossed, and which recovered. Pure post-processing of the analyst-supplied CPM snapshots; no additional schedule logic runs here.

| Activity | Min TF | Max TF | First window at TF 0 or below | Recovery | Slip velocity |
| --- | --- | --- | --- | --- | --- |
| BLD-ERECT | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| BLD-ROOF | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| CIV-BASE | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| CIV-BKF | +2 wd | +2 wd | never | none | 0 wd per window |
| CIV-CURE | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| CIV-EXC | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| CIV-MUD | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| CIV-SLAB | +2 wd | +2 wd | never | none | 0 wd per window |
| CIV-WALL | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| COM-DEMOB | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| COM-FLUSH | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| COM-FUNC | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| COM-LOOP | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| COM-PERF | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| ELE-CABLE | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| ELE-COND | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| ELE-MCC | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| ELE-TERM | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| MS-CONC | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| MS-ENERG | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| MS-NTP | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| MS-SC | 0 wd | 0 wd | Baseline | none | 0 wd per window |
| PRE-PERMIT | 0 wd | 0 wd | Baseline | none | 0 wd per window |

Caveat (cite in any expert report): Float burndown is post-processing of analyst-supplied CPM snapshots. Accuracy depends on the quality of the underlying schedule updates. Recovery events (TF increase) may reflect legitimate scope removal, schedule optimization, or activity deletion, and the register does not say which. Slip velocity is a linear average; actual burndown may be non-linear. The per-activity float-timeline presentation is not yet published in AACE/SCL literature; it is disclosed here as a CPP enhancement to the cited observational method.

Method: compute_float_burndown (engine v2.9.52). The register covers every critical and near-critical activity (TF at or below 5 working days in any window); none are omitted.

A-06   Cumulative Activity Slip Register

26 activities had their finish date move across the windows analyzed. Slip values are signed and summed across all windows per activity (positive = late).

| Code | Activity | Total Slip | Windows | CP at End |
| --- | --- | --- | --- | --- |
| MEC-PIPE | Internal Process Piping Install | +21 wd | 3 |  |
| MEC-VALVE | Valve and Actuator Install | +21 wd | 3 |  |
| MEC-TEST | Hydrostatic Test Process Piping | +21 wd | 3 |  |
| ELE-COND | Conduit and Cable Tray Rough-In | +21 wd | 3 |  |
| ELE-MCC | Set MCC and VFD Line-Up | +21 wd | 3 |  |
| ELE-CABLE | Power and Control Cable Pull | +21 wd | 3 |  |
| ELE-TERM | Terminate and Point-to-Point Check | +21 wd | 3 |  |
| MS-ENERG | Permanent Power Energized | +21 wd | 3 |  |
| COM-FLUSH | System Flush and Chlorination | +21 wd | 3 |  |
| COM-LOOP | Instrument Loop Checks | +21 wd | 3 |  |
| COM-FUNC | Functional Testing All Modes | +17 wd | 3 |  |
| COM-PERF | Performance and Capacity Demonstration | +17 wd | 3 | Yes |
| COM-DEMOB | Demobilize and Turnover Documentation | +17 wd | 3 | Yes |
| MS-SC | Substantial Completion | +17 wd | 3 | Yes |
| CIV-WALL | Form Reinforce and Pour Wet Well Walls | +15 wd | 2 |  |
| CIV-CURE | Wall Cure and Strip Formwork | +15 wd | 2 |  |
| MS-CONC | Concrete Structure Complete | +15 wd | 2 |  |
| CIV-BKF | Backfill and Compact Around Structure | +15 wd | 2 |  |
| CIV-SLAB | Grade Slab and Equipment Pads | +15 wd | 2 |  |
| MEC-SET | Set Pump Skids and Grout Baseplates | +15 wd | 2 |  |
| BLD-ERECT | Erect Pre-Engineered Building Frame | +15 wd | 2 |  |
| BLD-ROOF | Roof Deck and Membrane | +15 wd | 2 |  |
| BLD-CLAD | Wall Cladding and Flashing | +15 wd | 2 |  |
| BLD-DOOR | Overhead Doors and Louvres | +15 wd | 2 |  |
| ELE-PROC | MCC and VFD Fabrication and Delivery | +12 wd | 1 |  |
| CIV-BASE | Form Reinforce and Pour Base Slab | +8 wd | 1 |  |

Table shows all 26 activities (full register). Delay_Drivers.csv carries the same data in machine-readable form.

A-07   Concurrent Delay Analysis

Where Owner-caused and Contractor-caused delays overlap on the critical path, concurrent delay treatment applies. The slip register flags every CP activity that slipped in each window; the responsible-party column identifies periods where attribution is Owner on one CP activity and Contractor on another within the same window.

Warn [FILL IN: For each concurrent period identified in the slip register, document: (a) the period dates, (b) the Owner-attributed delay event, (c) the Contractor-attributed delay event, (d) the apportionment method applied (Dominant Cause / Time Apportionment / Malmaison), and (e) the resulting allocation of delay days. Reference the contract's concurrent delay clause if one exists.]

A-08   Attribution by Responsible Party

The position by party cannot be stated: 17 slip-days are unattributed. Complete attribution before signing this report.